## Sheet2
S/N | ACTIVITY | REQUIREMENTS | START DATE | END DATE | STATUS | REMARKS
1 | MODIFING INTERNAL AUDIT PAGE TO BA | BA DIRECTOR MSG | 2018-10-17 | 2018-11-02 | DONE WAITING FOR REVIEW | WAITING FOR REQUREMENTS FOR THE FINAL TOUCHS
2 | TO CREATE VERIFICATION FORM FOR IC | FORM INPUT VALUES FROM IC MNG | 2018-10-17 | 2018-11-02 | DONE WAITING FOR REVIEW
3 | TO CREATE MEET OUR TEAM PAGE | PICTURE & SHORT INFO OF BA AND SUB-DEPT. LEADERS | 2018-10-17 | 2018-11-02 | DONE WAITING FOR REVIEW
4 | TO CREATE GRAPHIC VISUALIZATION PAGE RISK | RISK INDICATORS DATA | 2018-10-17 | 2018-11-02 | DONE WAITING FOR REVIEW
5 | TO CREATE GRAPHIC VISUALIZATION PAGE COMPLIANCE | COMPLIANCE INDICATORS DATA | 2018-10-17 | 2018-11-02 | DONE WAITING FOR REVIEW
6 | TO ADD WHISTLE BLOWER HOT LINES LINK | PHONE & EMAIL | 2018-10-17 | 2018-11-02 | DONE WAITING FOR REVIEW
7 | TO CREATE POLICY AND PROCEDURE PAGE | PDF, XLS, OR WORD FILE FORMAT OF SOPs | 2018-10-17 | 2018-11-02 | INPROGRESS WAITING FOR DOCUMENTS
8 | TO MODIFY DEPARTMENTAL LIST PAGE | LIST OF SUB-DEPT IN BA | 2018-10-17 | 2018-11-02 | DONE WAITING FOR REVIEW

## Sheet3
S/N | OBSERVTION | RECOMMENDATION